## Slide 1: Cybersource & Infinity Corp : Case study Understanding
Acquirer
Payment methods
Issuer
VisaNet
Other Networks
Acquirer
Payment methods
‘ABC’ Payment system
Issuer
VisaNet
Other Networks
Migrated Payment System – ‘CyberSource’
Legacy Payment System – ‘ABC’
Acquirer

## Slide 2: Cybersource & Infinity Corp : Case study Assumptions
04
05
03
Migration is required predominantly at back-end with limited impact on front-end (Merchant’s CRM/SAP/ERP)
CyberSource’s partner ecosystem covers the existing partners of Infinity Corp (payment methods, payment networks etc)
06
07
CyberSource has pre-built integrations with various payment channels.
02
01
Initial Migration Readiness Pre-assessment is done (viability check)
Purchase Order & Licenses, subscription, Payment Methods in place
CyberSource payment system is inherently compliant with PCIDSS & no changes are required in its or Acquirer’s system.
Infinity Corp’s payment terms with ABC payment system organization is on ‘per transaction’

## Slide 3
Project Alpha

## Slide 4
Vision
Scope
Migration
Strategy
Project
Dashboard
Governance
& Change Management
Risk Model
06
05
04
03
02
01
Project Alpha : Agenda
07
Next Steps
Notes: Presenting the guiding principles of this program in terms of Vision and Scope
We’ll then have a quick look at the proposed Migration Strategy & High Level Plan
To secure the Project lifecycle, we’ll have a little discussion on the Handshake scenarios, Key Go-Live considerations, and overall Governance aspect of the program – stressing upon the Reporting, Risks, Change & Communication.

## Slide 5: Partnering the infinity Corp’s vision
To serve as a trusted partner to our clients by responsibly providing financial services that enable growth and economic progress
Cybersource Payment Management System – A modular Payment platform
We keep up with Consumer’s demands and stay ahead in payment technology & innovation
We take care of all your payment need & process it security and leave you to take care of your core business
Infinity Corp’s Vision
Notes: Our program would revolve around the foundation of establishing a long term partnership with your organization, resulting in your business and financial growth enablement via the activation of Cybersource solutions.
So, I would consider Migration Project as first and imp stepping stone in our long term relationship
Also, Being the industry leaders in providing Payment solutions/services, Cybersource is a natural fit for your business aspirations.

## Slide 6: Partnering Infinity Corp & Cybersource Expanded Portfolio
Compliance Requirements
Security by Visa
Futuristic &
Innovative
Accelerate Digital Capabilities
Seamless Payment Experience
Customer Focused
Speed of Response
Globalization
Modular Framework
Legacy Payment System
Secure & Innovative Digital Payment Arena
Notes: What I meant from ‘being a natural fit’ is that – our solution encompasses the true sense of becoming a globalised business by benefitting from our own coverage across 190 countries and vast payment channels. The Modular framework further helps in accelerating the digital transformation commerce through seamless payment experience. And the whole digital experience also stands at the strong pillars of Information & Data Security, and Legal Compliance requirements.

## Slide 7: Partnering Infinity Corp & Cybersource Project CharteR
Objective
Migration of existing legacy payment system to flexible and modular Payment management system which will also cater to Infinity Corp’s unique payment needs.
Switching ‘ABC’ Payment System to CyberSource Visa Payment management System.
Scope
Stakeholders
Seamless migration of Payment Management system with zero downtime.
Maintaining Data integrity & Data privacy of existing & new subscribers (Merchants)
Secure the payment flow from frauds.
Scaling the needs of Merchants to accept all online, in-person, via mobile payments from around the world.
Provide an insight of various payment methods & shopper’s preferences.
Infinity Corp
ABC Payment System
Issuers
Existing & Potential Subscribers
Deliverables
Successful migration of Payment system for entire APAC region with ‘0’ downtime.
Integrated Anti-fraud solutions and prevention tools.
Complaint system (PCI, GDPR)
Expanded reach to payments across channels and geographies within ‘2 sec’
Dashboard for multi-channel payment view for reconciliation & Shopper's preference.
Notes: A glimpse on the Project Charter. We are calling out the Objective of the program as Migration of Payment Mgmt System, along with some inclusions of Scope and Deliverables.
The Scope largely highlights the needs of having a seamless migration with Zero business disruption, secured payment flow covering Data integrity & privacy. The migrated payment system should additionally support fraud management, compliance with PCI , customer information management and advance reporting.
Deliverables defined are in-line with the agreed scope.
Key stakeholders as per initial understanding would be
IT team of infinity corp handling Merchant’s data and ABC payment system.
Program Management & IT Team of ABC payment systems
Issuer Banks
Also we would be considering all existing & potential Merchants of Infinity corp as our stakeholders too.

## Slide 8: Partnering infinity Corp & Cybersource Migration Strategy
Amalgamation of multiple Migration approaches
01
02
03
04
02 - Parallel Running
Phased approach Region wise:
    South East Asia
    Middle East
    North Asia
    South Asia
Synchronization
Strategy 04
- Synchronisation approach of Cyber source & ‘ABC’ payment system
01 - Big Bang Cutover
Authorization
Data Migration
Iterative Approach 03
Work streams for Payment Methods
Integration with Infinity Corp’s system
Notes: Moving to the core of the presentation - I would be covering the Migration Strategy in three folds. Presenting the high level strategy in this slide which is the amalgamation of Big Bang, Parallel and Iterative cutover.
Strategy is to take one region at a time (in iterative mode), migrate the data and enable new payment system for as-is features (in a big bang and parallel way) and once the CyberSource payment system is up and running, integrate other required features like anti-fraud solution, advanced reporting etc
We will consider Synchronization with legacy payment system for exceptional scenarios, and that would be for a certain duration post the cutover.
And iterative plan is made for geographies across APAC. This division is considered based on the assumption of # of merchants in that region, Shopping index, footfall in mcommerce and digital commerce and overall commerce revenue figures (till date)

## Slide 9
Assessment
Migration Factory
Hyper Care
Data Migration
Authorization
anti-Fraud Solutions
Hybrid whole
Pre-Migration
Migration
Steady State
CyberSource
Planning & Assessment
Migration approach
Team Requirement
Tools & Environments
Fall Back Approach
Legacy Wrapper Approach
Training & Communication Approach
Decommission the old system
100% SLA Ownership
Key Go-Live Considerations
Activate Fall Back Approach & Sync with Legacy System
Migration Blueprint as per business requirement (covering detailed scope, configuration management, security requirements)
Constant Monitoring & Controlling
Decommission ‘ABC’ for Card
Decommission ‘ABC’ for Digital Wallet
Decommission ‘ABC’ for Other Payment Methods
Integration with Acquirer System
Other services
(Reporting, Data Insights etc)
Partnering infinity Corp & Cybersource Iterative Migration Plan
D
B
T
R
I
legends
Notes: Moving on, I would also like to give you a bird’s eye view on how the Plan per region will move ahead in an Iterative way. Our team is working on the finer details of the plan as we speak, but this is to give you a fair idea of what to expect when we start the core migration.
For every region, we will do our extended study & planning in Pre-migration phase. In Migration factory, we would be starting with creating Migration blueprint based on technical analysis and then follow the SW life cycle process of design, build, test and roll out.
On the top are the set of boxes depicting the Big Bang roll-out, sliced per the ‘Payment Method’. While this foundation is being readied, the Data Migration will kick in for Cards, followed by Digital Wallet, and finally concluding with all other payment methods. The roll-out’s are sequenced, but the preparatory activities are all happening in parallel.
The advantage offered by the approach is the efficient and fast-tracked go-to market which would help in
derisking
maintaining agility & speed
Constant learning from previous & taking immediate actions for next
Financial savings and
Zero business disruption

## Slide 10: Partnering infinity Corp & Cybersource Project Schedule Plan
 | 2021 |  |  |  | 2022 |  |  | 
 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Go-Live Factors |  |  |  |  |  |  |  | 
Middle East |  |  |  |  |  |  |  | 
South East Asia |  |  |  |  |  |  |  | 
North Asia |  |  |  |  |  |  |  | 
South Asia |  |  |  |  |  |  |  | 
Pre-Assessment
Pre-Assessment
Change Management, Governance, Communication & Training
Migration factory
Hyper Care
Migration factory
Hyper Care
Decommission “ABC”
Monitor & Hand-over
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Monitoring & Control – Scope, Cost, Time, Quality, People, Stakeholder
Risk Management – Mitigation & Contingencies
Go-Live
Cards
Go-Live
Digital Wallet
Go-Live
Other Payment Channels
Decommission “ABC”
Pre-Assessment
Migration factory
Hyper Care
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Decommission “ABC”
Pre-Assessment
Migration factory
Hyper Care
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Decommission “ABC”
Integrate Fraud management
Fraud management & Reporting
Fraud management & Reporting
Fraud management & Reporting
Notes: This is another glimpse of the timeline plan covering the phases of the project for each region, and showing the interconnectivity between them as well so that the macro level activities like Monitoring, Risk & Change mgmt., and Communications are being injected and tracked at the right times throughout the project lifecycle.
The overall schedule plan is devised based on our agreement during SoW.

## Slide 11: Partnering Infinity Corp & Cybersource Handshaking Scnearios
Determining the Scope
Pre-Assessment
Ensuring Migration is viable
Understand Business model (Merchants, Payment networks)
Understand Security, Compliance & special requirements
Initial insights on data (volume, peak load etc)
Migration Readiness Assessment & Planning
Staging Environment
SLA’s & Tolerance
Fall Back & Legacy Wrapper Plan
Mapping of all existing & potential dependencies
Migration Factory
Migration approach & Schedule
Small scale simulations run with Infinity Team
Ensuring Communication, Change, Risk & Governance plans are functioning
Constant reporting on KPIs & SLA’s
Change Management for Merchants, Payment Networks
Steady State
Change management within Infinity
Configuration management (inc Artifacts)
Sign offs from designated/Substitutes
Go-Live
Constant reporting on traffic statistics & KPIs post migration
Communication plan for Go-Live
Master Plan for all of the PMP knowledge areas.
Mitigation Strategies
Indication for Decommissioning Legacy System
Activate Communication Plan for Fall Back
Pre & Post validation Outcome result
Success Party
Notes: While we lay down the principles of project approach and migration plans, one thing which we must keep into consideration for Detailed Planning is the constant bridging of information between Infinity Corp and Cybersource teams.
As both the teams collaborated in the Pre-assessment phase to draw the scope and viability guidelines, the same association would continue across the project lifecycle.
In the phase of Readiness Assessment & Planning, we would need to agree on the schedules, dependencies and SLA’s. During the Actual Migration phase, we’ll have to start rolling out the Communications, Change Plans, Simulation Runs with you and your team in the driving seat. Towards the Steady state phase, while we would ensure a stabilised migration outcome, we’ll need your sign-off’s on achieved milestones

## Slide 12: Partnering infinity Corp & Cybersource Go-Live Considerations
Is the System ready?
Health of project.
Entry Exit criteria’s met
Test & Defect Reports
Sign off parameters
Is the infrastructure ready?
Cyber Source & Infinity Corp’s
Network, processing speed
Storage capacity
Interfaces ready?
(e.g digital wallets)
Are the timings for cutover schedule reasonable.
Do interfaces need dry runs.
Are the users ready?
Changes analysed & Communicated.
Change Management employed.
Regular Reporting on SLAs & Risks
Sufficiently trained Users on new system.
Is the plan to handle early warnings ready?
Continuous monitoring
Mitigation & Contingency Plans
Is there fall back plan?
Workaround processes.
Cutover abortion plan Cutover extension plan
Fall back plan tested.

## Slide 13: Partnering infinity Corp & CYbersource Project Dashboard
Migration Status Dashboard
0.95
SPI
(Schedule Performance Index)
$20,000.00
Planned Value
0.98
CPI
(Cost Performance Index)
$18,000.00
Planned Value
Region Wise Completion Status
Phase wise completion status of “South Asia”
Phase wise % completed
Project Performance
Highlights
Chart: Cost Distribution Plan : Region wise
| South Asia | North Asia | South East Asia | Middle East
Pre-Assesment | 0.1 | 0.03 | 0.03 | 0.03
Migration Factory | 0.25 | 0.15 | 0.15 | 0.15
Hyper Care | 0.05 | 0.02 | 0.02 | 0.02
South Asia
Data Migration
- Cards
5441
45254
South Asia
Data Migration
- Digital Wallet
South Asia
Cads Transaction successful Rate
99.5%
North Asia
Simulation
Success for Cards
100%
Lowlights
South Asia : Data Migration for Cards Successful. Sign off received.
South Asia : Data Migration for Digital Wallet is successful.
Assessment & Planning completed for all regions
South Asia : Delay of 2 business days in data migration of Cards
South Asia : Unsuccessful transaction on first day.
Notes: This is just a sample Dashboard designed for this project. On regular basis we will be showing you the actual status of the migration with real numbers and success %age. I willensure to maintain transparency with everyone on progress, activemenets as well as lowlights.

## Slide 14: Partnering infinity Corp & Cubersource Effort Estimation & Distribution Plan
Chart: Effort Distribution : CyberSource & Infinity Corp
| CyberSource | Infity Corp
 | 0.85 | 0.15
Chart: Effort Estimation Per Phase
| Pre-Migration | Steady State | Migration
 | 20 | 20 | 60
Notes: Let me also take you through the effort estimation for this project. As we see, Migration factory takes up maximum of our effort. However on other hand, we will be able to maintain the pace of this program as our inherent features like Authorization, Anti-Fraud Solution, and Customer information management would take rather less effort.
The another graph depicts the effort requirements from Infinity Corp for this successful collaboration

## Slide 15: Partnering infinity Corp & Cybersource Governance & communication management
Steering Committee(Bi-Monthly)
Set Strategic Direction
Strategic & Business risk assessment & monitoring
Discuss overall relationship & Service-level performances
Engagement Review (Bi-Weekly)
Evaluate Performance on service levels & Review health of Project.
Current & Future Risk Profile
Program CR Tracker
Schedules and cost controls
Review of Change, Risk management Plan
Huddle (Daily)
Track individual activities
Resolve transactional & migration issues
Validation & Defect Status
Operational, projects, Functional risk assessment & mitigations.
Push Communication (Milestone)
To Merchants, Payment Networks
Dry Run Schedule
Updates to install
Migration Go-Live Schedule
HyperCare Plan
Post Go Live support
Business Sponsor
Business Leads
IT Head, Project Manager, Leads
IT Track Leads
Project Manager & IT Teams
Comm Teams
Merchants
Business Leads,
IT Track Leads
Program & Project Managers, Leads
Project Manager, Leads
IoT Testing Team
CyberSource
Tactical
Strategic
Proposed Governance Model
Infinity Corp
Notes: We’ll incorporate a well-established governance process for the whole duration of the programme. We have identified all stakeholders at different levels of hierarchy, and their counterparts in our organisation have been mapped together. We’ll be running different forums at each level to ensure proper cadence and tracking.
The steerco will be run between the Business sponsor/lead from Infinity and Programme lead of Cybersource, once a month.
The Engagement or the Project review between the Head of IT and our Program/Project Leads will be a fortnightly affair, covering project health, schedules and cost review, and discussion on roadblocks if any
Each communication layer would include risk identification, assessment and tracking as part of the agenda.
Not to forget the Push communications that would be sent to all Partners & Stakeholders on every milestone as per the communication plan. Idea is to keep them informed & at times involved in Dry run schedules, Post-Go Live Support etc.

## Slide 16: Partnering infinity Corp & Cbersource Change management Strategy
Restricted payment channel options
Infosec vulnerabilities
Transaction rejection across networks
Quality & Compliance
1
Real-time Global Tax Calculation
Fraud Management
Recurrent Payment Acceptance
Greater Tax Jurisdiction Coverage
Major Card Network Support
Why the Change
What will Change
Impact per Role
Change Approach
Current Challenges
Benefit Realisation
Opportunity
Need, Challenge, Opportunity
Interface, Payment Flow,
UI, Access, Additional Authentications
Training, Tutorials, Self Help, Hypercare
Notes: Moving to the next slide which is an overarching strategy for Change Management, this is also one of the most important activities that has to run throughout the entire program starting with fundamental thought process - Why this change. Having buy-ins from key stakeholders is equally important for success as the success of migration itself.
So, underneath Change management process, we will be focusing on evaluating the impact on stakeholders.
And to make them aware about what kind of changes are planned, how it would impact and what benefits can be reaped with this migration.
Some of the planned approaches for change management are - Training, Tutiorial and self –help documentation for Merchants and Partners. The plan would be monitored and measured on regular basis and if needed timely amendment will be proposed.

## Slide 17: Partnering infinity Corp & Cybersource Risk Management Plan
Identification of Risks
Questionnaire as tool
Deck-based risk assessment, Facilitated workshops, Management review
Registering risk in qualitative term
Identify Cause & Qualitative consequences
Assessment of Risks
Risk Assessment Matrix &
Risk Rating
Identifying & assessing effectiveness of controls
Risk Review Board
Residual risks & its consequences.
Treatment of Risks
Analyse Risk Appetite
Risk Response plan
(Threat & Opportunities)
Re-assess Risk Funding
Forecast risk analysis
Monitoring of Risks
Re-assessment
(Secondary, New Risks)
Periodic reviews
(Governance Plan)
Continuous Improvement
Analysis of risks
(Variances, Contingency reserves)
Notes: By now, We have covered the high level approach – a very hgih level projet schedule, change management and comm startegies which is getting detailed out as we speak.
Now we also need to understand the need of de-risking the whole project while doing Risk management activities. This is going to be one of the most crucial activity for overall project life cycle and for that both the teams will jointly work on identifying, assessing, responding and monitoring the first hand risks, secondary risks and also residual risks.

## Slide 18: Partnering infinity Corp & Cybersource project Alpha : Beginning the Journey…..
01
02
Detailed Project Plan & Vetting with Infinity Corp’s Project Team
Workstream – Migration Groups & define RASIC
03
04
Ramping the Team & Resources (Environment, Tools etc)
Pre-Migration Validation Preparation
Notes: Before I move on to the next steps, I would seek your feedback on this high level project plan so that we can formally kick off the Migration project with you.

## Slide 19: Thank You!
Shilpa Narang
(123) 456-7890
CyberSource Visa
Notes: © Copyright PresentationGO.com – The free PowerPoint and Google Slides template library