## Slide 1: Cybersource & Infinity Corp : Case study Understanding
Acquirer
Payment methods
Issuer
VisaNet
Other Networks
Acquirer
Payment methods
‘ABC’ Payment system
Issuer
VisaNet
Other Networks
Migrated Payment System – ‘CyberSource’
Legacy Payment System – ‘ABC’

## Slide 2: Cybersource & Infinity Corp : Case study Assumptions
04
05
03
Migration is required predominantly at back-end with limited impact on front-end (Merchant’s CRM/SAP/ERP)
CyberSource’s partner ecosystem covers the existing partners of Infinity Corp (payment methods, payment networks etc)
06
07
CyberSource has pre-built integrations with various payment channels.
02
01
Initial Migration Readiness Pre-assessment is done (viability check)
Purchase Order & Licenses, subscription, Payment Methods in place
CyberSource payment system is inherently compliant with PCIDSS & no changes are required in its or Acquirer’s system.
Infinity Corp’s payment terms with ABC payment system organization is on ‘per transaction’

## Slide 4
Vision
Scope
Migration
Strategy
Project
Dashboard
Governance
& Change Management
Risk Model
06
05
04
03
02
01
Agenda
07
Next Steps

## Slide 5: Partnering the infinity Corp’s vision
To serve as a trusted partner to our clients by responsibly providing financial services that enable growth and economic progress
Cybersource Payment Management System – A modular Payment platform
We keep up with Consumer’s demands and stay ahead in payment technology & innovation
We take care of all your payment need & process it security and leave you to take care of your core business
Infinity Corp Vision

## Slide 6
What is in store for you:
Expanded Portfolio of solutions with rich partnership
Compliance Requirements
Security by Visa
Futuristic &
Innovative
Accelerate Digital Capabilities
Seamless Payment Experience
Customer Focused
Speed of Response
Globalization
Modular Framework
Legacy Payment System
Secure & Innovative Digital Payment Arena
Notes: Business to products to customers : Enabling of better products and customer insights
Business to Assets : Enabling transformational optimization
This helps in
Manage, Analyze & Correlate
Collect, Store and Manage multi-faceted data from variety of test points
Transform test and defects data into customer, product, service insights
Use analytics to create self aware, auto healing, intelligent systems and optimize performance of overall product.
Institutionalize & Optimize
Transform testing from reactive to predictive preventive
Institutionalize remote product management, predictive and preventive maintenance
Optimize Operations continually

## Slide 7: Partnering Infinity Corp & Cybersource Project CharteR
Objective
Migration of existing legacy payment system to flexible and modular Payment management system which will also cater to X’s unique payment needs.
Switching to X payment system to Cybersource Visa Payment management System.
Scope
Stakeholders
Seamless migration from A payment system with zero downtime.
Maintaining Data integrity & Data privacy of existing & new subscribers (Merchants)
Scaling the needs of Merchants to accept all online, in-person, via mobile payments from around the world.
Secure the payment flow from frauds.
Provide an insight of various payment methods & shopper’s preferences.
Provides 24/7 support for the implemented payment management system.
All existing Subscribers
All new subscribers
‘A’ payment system
X
Issuer Banks
Deliverables
Successful migration of ‘ABC’ payment system with ‘0’ downtime of entire APAC region
Integrated Anti-fraud solutions and prevention tools.
Expanded reach to payments across channels and geographies within ‘2 sec’
Dashboard for multi-channel payment view for reconciliation & Shopper's preference.
Complaint system (PCI, GDPR)

## Slide 8
Determining the Scope
Pre-Assessment
Ensuring Migration is viable
Understand Business model (Merchants, Payment networks)
Understand Security, Compliance & special requirements
Get initial insights on data (volume, peak load etc)
Migration Readiness Planning & Assessment
Master Plan for all of the PMP knowledge areas.
Configuration management (inc Artifacts)
Tools to monitor health of system & agreed SLA’s.
Fall Back & Legacy Wrapper Plan
Mapping of all existing & potential dependencies
Migration Factory
Migration approach & Schedule
Pre-Migration Tests as required/planned
Ensuring Communication, Change & Governance plans are functioning
Migrate
Ensuring monitoring systems function as expected
Hyper care
Integrate new, special features
Monitor & Ensure SLA’s are met
Go-Live – Phase wise
Sign offs from designated
Hyper care
Steady State
Decommission Legacy System
Back-up of data from Legacy system
Risk management
Risk management
Notes: Master Plan : Designated sign-offs plan

## Slide 9: Partnering infinity Corp & Cybersource Migration Strategy
Amalgamation of multiple Migration approaches
01
02
03
04
02 - Parallel Running
Phased approach Region wise & Payment Method wise (Cards, Digital wallet, Other Payment Methods)
    South East Asia
    Middle East
    North Asia
    South Asia
Synchronization
Strategy 04
- Synchronisation approach of Cyber source & ‘A’ payment system
01 - Big Bang Cutover
For Authorization
For Visa Implementation
Iterative Approach 03
Data in both the systems.
Transition from Staging Area to final Target production state
End to End validations in parallel

## Slide 10: Partnering Infinity Corp & Cybersource Handshaking Scnearios
Determining the Scope
Pre-Assessment
Ensuring Migration is viable
Understand Business model (Merchants, Payment networks)
Understand Security, Compliance & special requirements
Initial insights on data (volume, peak load etc)
Migration Readiness Assessment & Planning
Staging Environment
SLA’s & Tolerance
Fall Back & Legacy Wrapper Plan
Mapping of all existing & potential dependencies
Migration Factory
Migration approach & Schedule
Small scale simulations run with Infinity Team
Ensuring Communication, Change, Risk & Governance plans are functioning
Constant reporting on KPIs & SLA’s
Change Management for Merchants, Payment Networks
Steady State
Change management within Infinity
Configuration management (inc Artifacts)
Sign offs from designated/Substitutes
Go-Live
Constant reporting on traffic statistics & KPIs post migration
Communication plan for Go-Live
Master Plan for all of the PMP knowledge areas.
Mitigation Strategies
Indication for Decommissioning Legacy System
Activate Communication Plan for Fall Back
Pre & Post validation Outcome result
Success Party
Notes: Master Plan : Designated sign-offs plan

## Slide 11
Assessment
Migration Factory
Hyper Care
Data Migration
Authorization
anti-Fraud Solutions
Hybrid whole
Pre-Migration
Migration
Steady State
CyberSource
Planning & Assessment
Migration approach
Team Requirement
Tools & Environments
Fall Back Approach
Legacy Wrapper Approach
Training & Communication Approach
Decommission the old system
100% SLA Ownership
Key Go-Live Considerations
Activate Fall Back Approach & Sync with Legacy System
Migration Blueprint as per business requirement (covering detailed scope, configuration management, security requirements)
Constant Monitoring & Controlling
Decommission ‘ABC’ for Card
Decommission ‘ABC’ for Digital Wallet
Decommission ‘ABC’ for Other Payment Methods
Integration with Acquirer System
Other services
(Reporting, Data Insights etc)
Partnering infinity Corp & Cybersource Iterative Migration Plan
Notes: Considerations : Volume of Data, Speed of data, Peak load, Bandwidth to serve all customers.
Also considered leading practices from other migration projects to come up with timeline

## Slide 12: Partnering infinity Corp & Cybersource Project Schedule Plan
 | 2021 |  |  |  | 2022 |  |  | 
 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
Go-Live Factors |  |  |  |  |  |  |  | 
Middle East |  |  |  |  |  |  |  | 
South East Asia |  |  |  |  |  |  |  | 
North Asia |  |  |  |  |  |  |  | 
South Asia |  |  |  |  |  |  |  | 
Pre-Assessment
Pre-Assessment
Change Management, Governance, Communication & Training
Migration factory
Hyper Care
Migration factory
Hyper Care
Decommission “ABC”
Monitor & Hand-over
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Monitoring & Control – Scope, Cost, Time, Quality, People, Stakeholder
Risk Management – Mitigation & Contingencies
Go-Live
Cards
Go-Live
Digital Wallet
Go-Live
Other Payment Channels
Decommission “ABC”
Pre-Assessment
Migration factory
Hyper Care
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Decommission “ABC”
Pre-Assessment
Migration factory
Hyper Care
Sync with ABC Payment System of Other regions
Monitor & Hand-over
Decommission “ABC”
Integrate Fraud management
Fraud management & Reporting
Fraud management & Reporting
Fraud management & Reporting

## Slide 13: Partnering infinity Corp & Cybersource Go-Live Considerations
Is the System ready?
Health of project.
Entry Exit criteria’s met
Test & Defect Reports
Sign off parameters
Is the infrastructure ready?
Cyber Source & Infinity Corp’s
Network, processing speed
Storage capacity
Interfaces ready?
(e.g digital wallets)
Are the timings for cutover schedule reasonable.
Do interfaces need dry runs.
Are the users ready?
Changes analysed & Communicated.
Change Management employed.
Regular Reporting on SLAs & Risks
Sufficiently trained Users on new system.
Is the plan to handle early warnings ready?
Continuous monitoring
Mitigation & Contingency Plans
Is there fall back plan?
Workaround processes.
Cutover abortion plan Cutover extension plan
Fall back plan tested.

## Slide 14: Partnering infinity Corp & CYbersource Project Dashboard
Migration Status Dashboard
0.95
SPI
(Schedule Performance Index)
$20,000.00
Planned Value
0.98
CPI
(Cost Performance Index)
$18,000.00
Planned Value
Region Wise Completion Status
Phase wise completion status of “South Asia”
Phase wise % completed
Project Performance
Highlights
Chart: Cost Distribution Plan : Region wise
| South Asia | North Asia | South East Asia | Middle East
Pre-Assesment | 0.1 | 0.03 | 0.03 | 0.03
Migration Factory | 0.25 | 0.15 | 0.15 | 0.15
Hyper Care | 0.05 | 0.02 | 0.02 | 0.02
South Asia
Data Migration
- Cards
5441
45254
South Asia
Data Migration
- Digital Wallet
South Asia
Cads Transaction successful Rate
99.5%
North Asia
Simulation
Success for Cards
100%
Lowlights
South Asia : Data Migration for Cards Successful. Sign off received.
South Asia : Data Migration for Digital Wallet is successful.
Assessment & Planning completed for all regions
South Asia : Delay of 2 business days in data migration of Cards
South Asia : Unsuccessful transaction on first day.

## Slide 15: Partnering infinity Corp & Cubersource Effort Estimation & Distribution Plan
Chart: Effort Distribution : CyberSource & Infinity Corp
| CyberSource | Infity Corp
 | 0.85 | 0.15
Chart: Effort Estimation Per Phase
| Pre-Migration | Steady State | Migration
 | 20 | 20 | 60

## Slide 16: Partnering infinity Corp & Cybersource Governance & communication management
Steering Committee(Bi-Monthly)
Set Strategic Direction
Strategic & Business risk assessment & monitoring
Discuss overall relationship & Service-level performances
Engagement Review (Bi-Weekly)
Evaluate Performance on service levels & Review health of Project.
Current & Future Risk Profile
Program CR Tracker
Schedules and cost controls
Review of Change, Risk management Plan
Huddle (Daily)
Track individual activities
Resolve transactional & migration issues
Validation & Defect Status
Operational, projects, Functional risk assessment & mitigations.
Push Communication (Milestone)
To Merchants, Payment Networks
Dry Run Schedule
Updates to install
Migration Go-Live Schedule
HyperCare Plan
Post Go Live support
Business Sponsor
Business Leads
IT Head, Project Manager, Leads
IT Track Leads
Project Manager & IT Teams
Comm Teams
Merchants
Business Leads,
IT Track Leads
Program & Project Managers, Leads
Project Manager, Leads
IoT Testing Team
CyberSource
Tactical
Strategic
Proposed Governance Model
Infinity Corp

## Slide 17: Partnering infinity Corp & Cbersource Change management Strategy
Restricted payment channel options
Infosec vulnerabilities
Transaction rejection across networks
Quality & Compliance
1
Real-time Global Tax Calculation
Fraud Management
Recurrent Payment Acceptance
Greater Tax Jurisdiction Coverage
Major Card Network Support
Why the Change
What will Change
Impact per Role
Change Approach
Current Challenges
Benefit Realisation
Opportunity
Need, Challenge, Opportunity
Interface, Payment Flow,
UI, Access, Additional Authentications
Training, Tutorials, Self Help, Hypercare

## Slide 18: Partnering infinity Corp & Cybersource Risk Management Plan
Identification of Risks
Questionnaire as tool
Deck-based risk assessment, Facilitated workshops, Management review
Registering risk in qualitative term
Identify Cause & Qualitative consequences
Assessment of Risks
Risk Assessment Matrix &
Risk Rating
Identifying & assessing effectiveness of controls
Risk Review Board
Residual risks & its consequences.
Treatment of Risks
Analyse Risk Appetite
Risk Response plan
(Threat & Opportunities)
Re-assess Risk Funding
Forecast risk analysis
Monitoring of Risks
Re-assessment
(Secondary, New Risks)
Periodic reviews
(Governance Plan)
Continuous Improvement
Analysis of risks
(Variances, Contingency reserves)

## Slide 19: Partnering infinity Corp & Cybersource Beginning the Journey…..
01
02
Detailed Project Plan & Vetting with Infinity Corp’s Project Team
Workstream – Migration Groups & define RASIC
03
06
Ramping the Team & Resources (Environment, Tools etc)
Pre-Migration Validation Preparation

## Slide 20
Internal | BSW | 09/04/2015 | © Robert Bosch Engineering and Business Solutions Private Limited 2015. All rights reserved, also regarding any disposal, exploitation, reproduction, editing, distribution, as well as in the event of applications for industrial property rights.
Collaboration for Test Activities
CI/CES52
Project Sponsor
Sr Project Manager
RBEI Coordinator
Test Lead
Overall Test coordination
Test and Defect review & Tracking
Test Planning & Closure activities
Purchase order
Billing
Proposal
Resource coordination
Monthly feedback
Test Execution and Defect Logging
Test Consultant
Test Case Design
Test Execution.
Defect retesting
Regression Testing
Service Designers
Prototyping
UI Design
Development
Unit Testing
Daimler
RBEI/BSW4
Customer
Coordinator
Requirements,
Tool Licenses and Environments.
Project Management
Task prioritization
External Developers
Service Designers
Prototyping
UI Design
Development
Unit Testing
Test Consultant
Test Case Design
Test Execution.
Defect retesting
Regression Testing
Bosch Developers

## Slide 21: Partnering infinity Corp & Cybersource Governance & communication management
Frequency
Organizer
Audience/
Recipient
Objective
Steering Committee
Monthly
Sr. Program Manager
CS & IC’s:
Business Sponsors
Business Leads
IT Track Leads
Financial Performance
Program Status
Huddle
Monthly
Weekly
Daily
Project Manager (PjM)
Project Manager
CS:
Business Leads
IT Track Leads
PjM & IT PMO
CS & ICs
Program & Project Managers
IT Track Leads
CS’s
Project SME’s
Project Team members
Strategic partnership & direction
Program Dashboard (RoI, SLA, KPIs)
Thought Leadership
Resolve critical escalations
Scrutinize program finances
Track program expenses
Analyze benefits realized
Program Status
Track specific RAID Log
Program CR Tracker
Schedules and cost controls
Track individual activities
Resolve transactional issues
Push Communication
Milestone
Sr. Program Manager w/ ICs Comm Team
Dry Run Schedule
Updates to install
Migration Go-Live Schedule
HyperCare Plan
Post Go Live support
Sr. Program Manager
CS’s & IC’s
Project Manager & IT Teams
Comm Teams
Merchants
Payment Network Teams

## Slide 22: Cybersource & Infinity Corp : Case study Assumptions
02
03
01
There is an established agreement in place between Infinity Corp & Merchants and there is no direct connection between CyberSource & Merchants
Migration is required mainly for back-end migration and has limited impact on front-end (at Merchant’s end)
ERP system used by Merchants is managed by Infiinity Corp
CyberSource’s partner ecosystem already covers the existing partners of Infinity Corp (payment methods, payment networks etc)
05
Infinity Corp’s payment terms with XYZ payment system company is on ‘per transaction’
06
Ready-to-use integrations are available from the CyberSource platform into the online and ecommerce tools that our customers already use
02
01
Initial Migration Readiness Pre-assessment is done (viability check)
Purchase Order has been received by CyberSource for the Migration & Added Services. Licenses, Subscription, payment method has been agreed on.
CyberSource payment system is inherently compliant with PCIDSS & no changes are required in its or Acquirer’s system.

## Slide 23
Governance Framework
Project Manager
Business Leads
IT Track Leads
IT PMO
Business SMEs
Engagement Manager
Business Sponsors
Business Leads
IT Track Leads
IT PMO
Project Manager
Project Team Members
Daily
Weekly
Monthly
Huddles
PMO Meetings
Steering Committee Meeting
Unilever
Vendor Partner
Deliverable: Steering Committee Report
Objective:
Strategic partnership and direction
Assess program status, ROI, risks, critical milestones
Thought Leadership
Resolve critical escalations
Deliverable: Status Reports
Objective:
Status and key metrics reporting
Escalation and risk management
Change management
Schedules and cost controls
Deliverable: Project Tracker
Objective:
Track individual activities
Resolve transactional issues
Coordinate with required stakeholders
Escalate as required

## Slide 24: Partnering infinity Corp & Cybersource Risk Management Plan
Identification of Risks
Sources of Risks
(Workshops,
Follow Governance Plan
Assessment of Risks
Risk Review Board
Severity & Priority Scale (3*3)
Registering the risk
Risk Funding
Risk Assessment Matrix
Risk Response
Risk Appetite
Response for Opportunities
Periodic Review as per Governance Plan
Monitoring the Risk
Residual, Secondary, New Risks
Analysis – variances, Contingency reserves

## Slide 25
Assumptions:
Agreement with ‘A’ payment system for migration of existing subscribers
Limited to Back-end migration & has no impact on front-end
Cybersource is partnered with existing .parners of X
“There is an inherent credibility that comes from working with Visa
Ready-to-use integrations from the Cybersource platform into the online and ecommerce tools that our customers already use
Value add:
We’ve been able to establish relationships with new services and organizations that are part of the Visa ecosystem, including other resellers, integration specialists and add-on technology partners

## Slide 26: Partnering infinity Corp & Cubersource Cost Distribution Plan
Chart: Estimated Cost Plan : Region wise
| South Asia | North Asia | South East Asia | Middle East
Pre-Assesment | 0.1 | 0.03 | 0.03 | 0.03
Migration Factory | 0.25 | 0.15 | 0.15 | 0.15
Hyper Care | 0.05 | 0.02 | 0.02 | 0.02

## Slide 27: Transition Approach

## Slide 28: Cybersource & Infinity Corp : Case study Understanding
Acquirer
Payment methods
Issuer
VisaNet
Other Networks
Acquirer
Payment methods
‘ABC’ Payment system
Issuer
VisaNet
Other Networks
Migrated Payment System – ‘CyberSource’
Legacy Payment System – ‘ABC’
Acquirer
Notes: This case study talks about a potential acquirer which, I would be referring by the name of “Infinity Corp” in my presentation. Infinity Corp wants to migrate away from their existing payment system i.e ABC payment system to ‘CyberSource” payment management system.
The entire payment flow would remain same in the migrated payment system. However CyberSource enables a single platform and has pre-built integrations with payment methods and payment networks. So, it acts as a Modular payment management system and supports extensive range of payment methods and international currencies, along with few value added services like Fraud management, PCI compliance
Infinity Corp is really looking forward for the success of this migration to a single platform as currently this acquirer is handling multiple issues across interconnected software’s and payment flow through complex integrated system.

## Slide 29
Discover Business needs:
  Business models of X acquirer.
  Agreements with Merchants
  Existing Payment System
Identify Migration Bubbles:
  right Migration Approach
  factors influencing switch migration.
  proper tools
  Team
  Training requirements
Iterative Migration Plan
Week 1
Week 2-3
Week 4-6
Week 7-8
Week 8 onwards..
Pre Migration
IOT Test Center Build
Steady State

## Slide 30
Iterative Migration Plan
Week 1
Pre Migration
Migration Factory
Steady State
Phase –III (North)
Phase –I (South Asia)
Phase –II (South-east)
Assessment ---Build ---Testing ---Implementation
Phase –III (Middle East)

## Slide 31
Pre Transition
Knowledge Acquisition
Handover & Stabilization
IOT Test Center Build
Steady State
Signed-off Transition Governance Model
Training plan, access/licenses/tools requirements
Transition plan and schedule
Test Strategy
Handover of existing documentation and test plans
Staffing plan
Establish offshore connectivity and validate access
Study Existing Process, guidelines, standards & policies and automation framework
Identify critical tasks
Finalize staffing requirements
Ramp-up capacity
Training plan implementation
Testing tools and test env. setup
Shadow & Reverse KT
Test Plan detailing
Test data setup and documentation
Baselining the test strategy
Implement Automation and Performance Test suites
Design and implementation of new test cases
Approved OLA/SLA
Process and Traceability Set up
Data analysis
Signed-off Engagement Model
Hybrid model
Independent Handling
Crowdsourcing framework in place
Piloting SLA Monitoring
Validating Test Cases and Test Results
SLA/KPI Tracking,
Implementation of governance and communication models
Monthly dashboard - Availability, SLA/ KPI,
Signed off test plan
Execution of test cases as per agreed timelines

## Slide 33: Key Go-Live Considerations
Is the System ready?
Health of project
Entry Exit criteria’s met
Test & Defect Reports
Sign off parameters
Is the infrastructure ready?
Acquirer’s network, processing speed and storage capacity to connect to Cybersource
Are the users ready?
Changes analysed & Communicated.
Sufficiently trained on new system
User knows how to deal with unforeseen issues,
Interfaces (digital wallets) ready?
Are the timings for cutover schedule reasonable.
Do they need dry runs.
Is the plan to handle early warnings ready?
Continuous monitoring
Mitigation & Contingency Plans
Is there fall back plan?
Workaround processes.
Cutover abortion plan (exceptional case)
Cutover extension plan
Fall back plan tested.
Are the Stakeholders ready?
Regular Reporting on SLAs & Risks
Communication Plan implemented.
Change Management employed.

## Slide 34
Iterative Migration Plan
Fall back scenarios
Legacy wrapping approach
Pre-Assesment
Migration Factory
Hyper Care
Parallel (Data Migration)
Big Bang (Authorization)
Big Bang
(anti-Fraud Solutions)
Parallel (End to End)
Hybrid whole
Pre-Migration
Migration
Steady State
Cybersource
Planning & Assessment
Migration approach
Team Requirement
Tool requirements
Fall Back Approach
Legacy Wrapper Approach
Training & Communication Approach
Decommission the old system
100% SLA Ownership
Key Go-Live Considerations
Activate Fall Back Approach & Sync with Legacy System
Migration Blueprint as per business requirement
Constant Monitoring & Controlling

## Slide 35: Project Schedule Plan
 | 2021 |  |  |  |  |  |  |  | 2022 | 
 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Go-Live Factors |  |  |  |  |  |  |  |  |  | 
Middle East |  |  |  |  |  |  |  |  |  | 
South East Asia |  |  |  |  |  |  |  |  |  | 
North Asia |  |  |  |  |  |  |  |  |  | 
South Asia |  |  |  |  |  |  |  |  |  | 
Pre-Assessment
Pre-Assessment
Change Management, Governance, Communication & Training
Migration factory
Hyper Care
Migration factory
Hyper Care
Pre-Assessment
Migration factory
Hyper Care
Sync with A Payment System
Decommission “A”
Monitor & Hand-over
Sync with A Payment System
Decommission “A”
Monitor & Hand-over
Decommission “A”
Monitor & Hand-over
Sync with A Payment System
Pre-Assessment
Migration factory
Hyper Care
Decommission “A”
Monitor & Hand-over
Sync with A Payment System
Monitoring & Control – Scope, Cost, Time, Quality, People, Stakeholder
Risk Management – Mitigation & Contingencies

## Slide 36
Iterative Migration Plan
Fall back scenarios
Legacy wrapping approach
Pre-Assesment
Migration Factory
Hyper Care
Phase –III (Data Migration)
Phase –I (Authorization)
Phase –II (Visa Interface)
Phase –IV (Overall)
Hybrid whole
Pre-Migration
Migration
Steady State
Cybersource
Planning & Assessment
Migration approach
Team Requirement
Tool requirements
Fall Back Approach
Legacy Wrapper Approach
Training & Communication Approach
Decommission the old system
100% SLA Ownership
Key Go-Live Considerations
Activate Fall Back Approach

## Slide 37: Project team
Design
(Migration Blueprint)
Deploy
(Automated Migration)
Develop
(Tool Enhancement)
Testing (Functional, System, Performance, Security)
Roll Out
(Acceptance Testing)

## Slide 38: Effort Estimation